## project plan
Week | Todo | Difficulty Estimation
2023-06-10 | Create new Git repo | Easy
| Create Trello board | Easy
| Create spreadsheet of project plan | Easy
2023-06-17 | Create two branches | Easy
| Run app on local env | Medium
| Run app on Azure | Medium
2023-06-24 | Set up GitHub Actions | Medium
| Test Github Action | Medium
| Create the App Service in Azure | Easy
| Test the app Services | Medium
| Set up the Azure DevOps pipeline | Medium
2023-07-08 | Create Diagram | Easy
| Screenshots | Easy
| Modified Readme file | Easy
| Record a video demo | Easy
7/14/2023 | upload to Youtube | Easy
Goals
Submit project
Q3 plan | Complete project
Yearly plan | Review the code, maintain it